## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | AI Based Healthcare Management System |  |  |  |  | INSTITUTE & DEPARTMENT NAME: | [6 empty] | A.P Shah Institute of Technology , IT
PROJECT GUIDE |  | Prof. Rujata Chaudhari |  |  |  |  | DATE | [6 empty] | 2-15-21
PROJECT CO GUIDE |  | Prof. Geetanjali Kalme
[13 empty] | PHASE ONE | [15 empty] | PHASE TWO | [13 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[9 empty] | WEEK1 |  |  |  | WEEK2 |  |  |  |  | WEEK3 |  |  |  |  | WEEK4 |  |  |  |  | WEEK5 |  |  |  |  | WEEK6 |  |  |  |  | WEEK7 |  |  |  |  | WEEK8 |  |  |  |  | WEEK9 |  |  |  |  | WEEK10 |  |  |  |  | WEEK11 |  |  |  |  | WEEK12
WBS NO. | TASK TITLE | TASK OWNER | START DATE | DUE DATE | WEEKS | % COMPLETE | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
1 | Project Conception and Initiation
1.1 | Research paper search | Pranav,Bhaskar,Shefali | 2020-01-22 | 2020-02-08 | 3 | 100% | bar: WEEK1 W to WEEK2 F
1.1.1 | Research paper finalization | Pranav,Bhaskar,Shefali | 2020-02-24 | 2020-02-26 | 3 | 100%
1.2 | Project Title | Pranav,Bhaskar,Shefali | 2020-02-28 | 2020-03-14 | 3 | 100% | bar: WEEK1 M to WEEK3 W
1.3 | Abstract | Shefali | 2020-03-13 | 2020-03-20 | 1 | 100% | bar: WEEK1 M to WEEK3 F
1.4 | Objectives | Pranav,Bhaskar,Shefali | 2020-03-22 | 2020-03-27 | 1 | 100% | bar: WEEK1 M to WEEK3 TH
1.5 | Literature Review | Bhaskar | 2020-03-28 | 2020-04-03 | 1 | 100% | bar: WEEK3 T to WEEK3 TH
1.6 | Problem Definition | Pranav | 2020-03-07 | 2020-03-12 | 1 | 100% | bar: WEEK3 F
1.7 | Scope | Bhaskar | 2020-03-07 | 2020-03-07 | 1 | 100% | bar: WEEK3 F
1.8 | Technology stack | Pranav,Shefali | 2020-03-07 | 2020-03-07 | 1 | 100% | bar: WEEK3 F
1.9 | Benefits for environment | Shefali | 2020-03-07 | 2020-03-07 | 1 | 100% | bar: WEEK3 F
1.1 | Benefits for society | Bhaskar | 2020-03-07 | 2020-03-07 | 1 | 100% | bar: WEEK3 F
1.11 | Applications | Pranav | 2020-03-07 | 2020-03-07 | 1 | 100% | bar: WEEK3 F
2 | Project Design
2.1 | Proposed System | Pranav,Bhaskar | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK3 M to WEEK5 F
2.2 | Design(Flow Of Modules) | Pranav,Bhaskar | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK3 M to WEEK5 F
2.3 | Activity Diagram | Bhaskar,Shefali | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 W to WEEK6 TH
2.4 | Use Case Diagram | Pranav,Shefali | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 W to WEEK6 TH
2.5 | Description Of Use Case | Shefali | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 T to WEEK4 M; WEEK5 W to WEEK5 F
2.6 | Modules | bar: WEEK5 W to WEEK5 F
2.6.1 | Module-1 | Pranav,Bhaskar,Shefali | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 TH to WEEK6 F
2.6.2 | Module-2 | Pranav | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK3 M to WEEK5 F
2.6.3 | Module-3 | Bhaskar | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 TH to WEEK5 F
2.6.4 | Module-4 | Pranav | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK3 M to WEEK4 M; WEEK5 W to WEEK6 F
2.7 | Preparation Of Report | Shefali | 2020-09-22 | 2020-10-09 | 2 | 100% | bar: WEEK4 W to WEEK5 F
3 | Project Implementation
3.1 | Module-1 | Pranav | 2020-10-05 | 2020-10-10 | 1 | 100% | bar: WEEK6 M to WEEK7 F; WEEK8 W to WEEK8 F
3.2 | Module-2 | Shefali | 2020-10-05 | 2020-10-10 | 1 | 100% | bar: WEEK7 W to WEEK8 F
3.3 | Module-3 | Bhaskar | 2020-10-22 | 2020-10-22 | 1 | 100% | bar: WEEK8 W to WEEK9 T
4 | Testing
4.1 | Architecture | Bhaskar | 2020-11-10 | 2020-11-17 | 1 | 100% | bar: WEEK9 M to WEEK11 F
4.2 | Prototyping | Pranav,Bhaskar,Shefali | 2020-11-15 | 11-15-20 | 2 | 100% | bar: WEEK9 M to WEEK11 F
4.3 | Development | Pranav,Bhaskar,Shefali | 2021-02-02 | 2021-02-05 | 2 | 100% | bar: WEEK9 M to WEEK11 F
4.4 | Testing | Bhaskar,Shefali | 2021-03-15 | 2021-03-17 | 2 | 100% | bar: WEEK9 M to WEEK11 F
4.5 | Cloud Server Allocation | Bhaskar,Shefali | 2021-03-18 | 2021-03-20 | 1 | 100%
4.6 | Multilingual System Implementation | Pranav | 2021-03-18 | 2021-03-21 | 2 | 100% | bar: WEEK9 M to WEEK11 F
4.7 | Implementation Of ChatBot | Pranav,Bhaskar,Shefali | 3-20-21 | 3-24-21 | 1 | 100% | bar: WEEK10 T to WEEK11 F
4.8 | Implementation Of Cloud Server | Pranav | 2021-04-10 | 2021-04-15 | 1 | 100%
4.9 | Design and implement Website | Pranav, Bhaskar,Shefali | 2021-04-21 | 2021-04-27 | 3 | 100% | bar: WEEK10 T to WEEK12 TH
5 | Results and Analyis
5.1 | Report Preparation | Bhaskar,Shefali | 2021-05-01 | 2021-05-10 | 2 | 100% | bar: WEEK10 W to WEEK11 M